## Methodology
Open monitoring data and treatment data in mapping software (e.g., Arc Online)
Filter treatment data for past 4 years
Prior to running through the primary tamarisk removal and Russian knapweed matrix, look at all photos of site if those are available
Open monitoring data and then run the site through TRO removal (if necessary, Russian knapweed, and abiotic matrix)
Record scores on the "List of Sites & scores" tab
Look through invasive species inventory. If there are species of concern (e.g., whitetop) make sure the site is listed in the "Schedule" tab
Include sites on the schedule tab if they need resprouts (either if a site has had initial removal in past few years or if the monitoring data indicates resprout treatments are needed)
List site for Russian knapweed at this point ONLY if it has been treated the prior year.
Do this for all sites and then at the end rank all of the sites with RK + abiotic and Initial Treatments + abiotic
Plug in the top sites for treatment in the schedule. Since it is hard to know how long this will take, additional sites can be adaptively added from the list.
Add any sites that have not been monitored to the 'schedule" tab as well (e.g., if there is a site that need initial tamarisk removal but hasn't been monitored.)
NOTES: This methodology will be slightly altered based on the type of monitoring data available.

## Abiotic criteria
Size:
CRITERIA | Y/N (Y=1, N=0) | Rank (1-5) | Weight | Total
Landowner/manager support (1 - no, 5 - strong support) |  |  | 3 | 0
Ease of access (1 - none, 2 - float access, 3 - horsepacking, 4 - hike required, 5 - road access |  |  | 3 | 0
Strike team weeks (5: <1, 4: 1, 3: 1-2, 4: 2, 5: >2) |  |  | 2 | 0
What is the cost in crew weeks? (5: 0 wk; 4: 1 wks; 3: 2 wks; 2: 3 wks; 5 >4 wks. ) |  |  | 2 | 0
Is there funding? Y/N |  |  | 3 | 0
Is there any permitting needed? (1 - long processes needed, 3- yes, but simple EA, 5 - no new permits needed) |  |  | 3 | 0
Is there a recreational benefit? (e.g, campsite, trail, boat ramp)(Y/N) |  |  | 2 | 0
Is this site part of a special project area? (Y/N) |  |  | 3 | 0
Total |  |  |  | 0

## Tamarisk and RO Treatment
Site: | Size:
CRITERIA | Y/N (Y=1, N=0) | Rank (1-5) | Weight (1-3) | Total
Are there any cottonwood galleries or clusters of box elders? (1 - none, 3 - four to seven trees over 10 ft., 5 - large gallery over ten mature trees with varied age classes) |  |  | 3 | 0
Relative cover of tamarisk or Russian olive? (5: 6-10%, 4: 11-20%, 3: 21-30%, 2: 50%, 1: >55%) If less than 5% = 0 |  |  | 3 | 0
What is the percent native cover? (1 - <20%, 2 - 41-50%, 3 -51-60% 4 - 60%-80% - 5-80%-100%) |  |  | 3 | 0
Sites meets passive revegetation for woody species - Y/N |  |  | 2 | 0
Has this site been treated in past years? Y/N |  |  | 3 | 0
Level of tamarisk defoliation (1 - dead, 3- moderate, 5 - green) (ignore for Russian olive) |  |  | 3 | 0
Presence of white crust on soil ( 1 - very prevelent 5 - none) |  |  | 1 | 0
Has there been active reveg at the site? (Y/N) |  |  | 3 | 0
Is there Russian knapweed on site? (5: none, 3: some, 1; yes-dense) |  |  | 2 | 0
Signs of grazing on site? (Y/N) |  |  | 1 | 0
Total |  |  |  | 0

## Russian knapweed
Site: | Size: |  |  |  | Notes
CRITERIA | Y/N (Y=1, N=0) | Rank (1-5) | Weight | Total
What is the percent native cover? (1 - <30%, 2 - 31-50%, 3 - 51% - 60% 4 - 60%-80% - 5-80%-100%) |  |  | 3 | 0
Sites meets passive revegetation for woody species - Y/N |  |  | 2 | 0
Has this site been treated in past 1-2 years? Y/N |  |  | 3 | 0
Relative cover knapweed? (1: >75%, 2: 40-60%, 3: 21-40%, 4: 11-20% 5: <11%) |  |  | 2 | 0
Presence of white crust on soil ( 1 - very prevelent 5 - none) |  |  | 1 | 0
Is there Russian thistle? (1: Yes - dense, 3: sparse, 5: none) |  |  | 1 | 0
Is there kochia on site? (1: Yes - dense, 3: sparse, 5: none) |  |  | 1 | 0
Is there cheatgrass (1: Yes - dense, 3: sparse, 5: none) |  |  | 1 | 0
Has active reveg occured at this site? (Y/N) |  |  | 3 | 0
What is the relative cover of tamarisk at this site? (1: >75%, 2: >50%, 3: 31-40%, 4: 21-30%:, 5: <20%) |  |  | 3 | 0
Signs of grazing on site? (Y/N) |  |  | 1 | 0
Total |  |  |  | 0

## List of Sites & Scores
Grand Junction Field Office: 2021
Reporting Polygon | RL/RR | Size (acres) | Overall score TRO | Overall Score RK | Abiotic Score | Re-sprouts | Spring weeds | Fall weeds | Active Revegetation | Meets Passive recruitment | Owner/manager | Notes